## Status Report
Status Report for [Name] - [Project Name]
Project |  | Status: (Red/Yellow/Green)
Date: | 2024-10-17 | Overall Status: | Green
Contact: | Cindy | Explanation:
Prepared By: | Cieniek
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
1 | Creater user profiles, token auth, and connected frontend with backend |  |  | Tested: | views in django
2 | Delete users from group |  |  | Tested: | crud api actions
3 | Edit the events |  |  | Tested: | crud api actions
ID # | Key Issues | Action Plan |  |  | Status
1 | User profiles and authentication |  |  |  | done
2 | Calendar CRUD |  |  |  | done
3 | Groups and Permissions |  |  |  | done
4 | News Component |  |  |  | done
Critical Milestones |  | Health | Due Date | Comment/Status
Authentication setup |  | 100%
Back-end |  | 100% | 2020-09-27
Business logic: resources, design justifications, tech stack, documentation |  | 100%
Front-end |  | 100% | 2024-10-13
Testing |  | 50%
Presentation slides |  | 0% | 2024-10-15
Extra requirements |  | 0%